## 01_Dashboard
MOVIELENS HYBRID RECOMMENDATION SYSTEM — PROJECT CONTROL DASHBOARD
[7 empty] | Status | Count
[7 empty] | Not Started | 25
PROJECT SNAPSHOT | VALUE |  | OWNER | TASKS | DONE | PROGRESS | In Progress | 0
Sprint Start | 2026-09-24 |  | Person 1 | 11 | 0 | 0% | Blocked | 0
Sprint Length | 10 |  | Person 2 | 8 | 0 | 0% | Done | 0
Total Tasks | 25 |  | Both | 6 | 0 | 0%
Completed | 0
Blocked | 0 | [5 empty] | Owner | Tasks | Done
Overall Progress | 0% | [5 empty] | Person 1 | 11 | 0
[7 empty] | Person 2 | 8 | 0
[7 empty] | Both | 6 | 0
PHASE | TASKS | DONE | PROGRESS |  | MANAGEMENT RULES
Phase 0 - Setup | 2 | 0 | 0% |  | 1) A task is DONE only when: code runs + output is correct + evidence exists + downstream can consume it. 2) Person 1 owns Data → Modeling → Evaluation → Serving Artifacts. 3) Person 2 owns MongoDB → API → Routing → Streaming → Serving Integration. 4) Mandatory handoffs: Artifact Contract, Real Serving Artifacts, Retraining/Promotion. 5) Any BLOCKED task must have a written blocker, owner, and next action.
Phase 1 - Data Foundation | 4 | 0 | 0%
Phase 2 - Analytics & Validation | 4 | 0 | 0%
Phase 3 - Modeling | 5 | 0 | 0%
Phase 4 - Online Serving | 2 | 0 | 0%
Phase 5 - Streaming | 2 | 0 | 0%
Phase 6 - Model Refresh | 2 | 0 | 0%
Phase 7 - Performance & Reproducibility | 2 | 0 | 0%
Phase 8 - Integration & Demo | 2 | 0 | 0%

## 02_Master_Plan
WBS | Phase | Owner | Task | Start Day | Duration | Start Date | Due Date | Priority | Status | % Complete | Dependency | Input | Step-by-step Work | Output / Deliverable | Definition of Done | Evidence | Handoff / Consumer | Manager Notes
0.1 | Phase 0 - Setup | Both | Lock architecture, repo, folder structure, config, naming conventions | 1 | 1 | 2026-09-24 | 2026-09-24 | Critical | Not Started | 0 | - | Final architecture + project requirements | 1) Create repo 2) Create folders 3) Create config 4) Agree naming/versioning 5) Verify both machines can run skeleton | Repo + README + config + agreed folder structure | Both members can clone/run skeleton; config paths work | README screenshot; repo structure; environment versions | Both
0.2 | Phase 0 - Setup | Both | Freeze data contract and serving artifact contract | 1 | 1 | 2026-09-24 | 2026-09-24 | Critical | Not Started | 0 | 0.1 | Architecture + MovieLens schema | 1) Freeze userId/movieId/rating/timestamp types 2) Freeze Popularity schema 3) Freeze Similar-Movie schema 4) Freeze ALS Top-N schema | Signed-off schema contracts | Person 2 can consume mock artifacts without manual edits | Schema document; sample JSON/CSV | Both
1.1 | Phase 1 - Data Foundation | Person 1 | Ingest MovieLens CSV with explicit PySpark schemas | 1 | 1 | 2026-09-24 | 2026-09-24 | Critical | Not Started | 0 | 0.1 | ratings.csv, movies.csv, tags.csv, links.csv | 1) Define StructType 2) Read CSV 3) Inspect schema 4) Count rows 5) Validate key columns | ratings_df, movies_df, tags_df, links_df | Schemas/types correct; row counts captured; no silent inference | Schema print; row counts; sample rows | 1.2
1.2 | Phase 1 - Data Foundation | Person 1 | Clean, transform and join core datasets | 2 | 1 | 2026-09-25 | 2026-09-25 | Critical | Not Started | 0 | 1.1 | Raw DataFrames | 1) Null checks 2) Invalid rating checks 3) Duplicate checks 4) Timestamp transform 5) Join by movieId 6) Log unmatched keys | Clean/enriched DataFrames | No unresolved critical quality issue; joins validated | Quality summary; before/after counts; join checks | 1.3
1.3 | Phase 1 - Data Foundation | Person 1 | Write Curated Parquet and read-back validation | 2 | 1 | 2026-09-25 | 2026-09-25 | Critical | Not Started | 0 | 1.2 | Clean DataFrames | 1) Write partitioned/bounded Parquet as appropriate 2) Read back 3) Compare counts/schema 4) Record path/version | Curated Parquet | Read-back succeeds; schema/counts consistent | Parquet paths; read-back output; row counts | Person 1 analytics + Person 2 streaming append target
1.4 | Phase 1 - Data Foundation | Person 2 | Create MongoDB serving schema using mock artifacts | 1 | 2 | 2026-09-24 | 2026-09-25 | High | Not Started | 0 | 0.2 | Serving artifact contract | 1) Create collections 2) Create indexes 3) Insert mock Popularity/Similar/ALS docs 4) Query by userId/movieId | MongoDB serving skeleton | Mock artifacts can be inserted/read with target access patterns | Collection list; index list; sample read-back | 2.4 / 3.1
2.1 | Phase 2 - Analytics & Validation | Person 1 | Build Spark SQL analytics and inspect execution plans | 3 | 1 | 2026-09-26 | 2026-09-26 | High | Not Started | 0 | 1.3 | Curated Parquet | 1) Create views/DataFrames 2) Run most-rated/genre/user/time queries 3) explain('formatted') 4) Capture Exchange/join/aggregate observations | Analytics results + execution-plan evidence | At least 2 meaningful SQL analyses + formatted plan interpretation | Query outputs; explain plan; screenshots | Report / evidence
2.2 | Phase 2 - Analytics & Validation | Person 1 | Implement MapReduce statistics and cross-check with Spark | 3 | 1 | 2026-09-26 | 2026-09-26 | Medium | Not Started | 0 | 1.2 | Clean ratings text/CSV or compatible input | 1) Mapper emits movieId -> (rating,1) 2) Combiner sums partials 3) Reducer computes total/count/avg 4) Compare Spark groupBy | MapReduce statistics | Reducer output matches Spark within expected tolerance | Mapper/reducer code; comparison table | Report / evidence
2.3 | Phase 2 - Analytics & Validation | Person 2 | Build Recommendation API skeleton + User History Check | 2 | 2 | 2026-09-25 | 2026-09-26 | High | Not Started | 0 | 1.4 | MongoDB mock serving store | 1) Define request contract 2) Read user_history 3) Return interaction_count/tier 4) Add basic response contract | Working API skeleton | Given userId, API returns valid history tier | API request/response samples; logs | 2.4
2.4 | Phase 2 - Analytics & Validation | Person 2 | Implement 0/Few/Enough history router with mock data | 3 | 1 | 2026-09-26 | 2026-09-26 | Critical | Not Started | 0 | 2.3 | API skeleton + mock artifacts | 1) 0 -> Popularity 2) Few -> Content + optional Popularity 3) Enough -> ALS + optional Content 4) Unit-test 3 cases | History-based switching logic | All three paths return candidates from correct sources | 3 test cases; routing logs | 3.2 / 4.2
3.1 | Phase 3 - Modeling | Person 1 | Create train/validation/test evaluation setup | 3 | 1 | 2026-09-26 | 2026-09-26 | Critical | Not Started | 0 | 1.3 | Curated ratings | 1) Choose fixed-seed or temporal split 2) Prevent leakage 3) Persist split metadata 4) Define relevant item threshold for ranking | train_df, val_df, test_df + evaluation rules | Split reproducible; no leakage; relevant-item rule documented | Split counts; seed/config; rule definition | 3.2 / 3.3 / 3.4
3.2 | Phase 3 - Modeling | Person 1 | Build Movie Mean and Popularity baselines | 3 | 1 | 2026-09-26 | 2026-09-26 | High | Not Started | 0 | 3.1 | Train data | 1) Movie Mean prediction 2) Global fallback 3) Popularity score 4) Create Popularity Top-N | Movie Mean baseline + Popularity Top-N | Predictions exist; Popularity Top-N valid and deterministic | Baseline metrics; sample Top-N | 3.5 / Person 2
3.3 | Phase 3 - Modeling | Person 1 | Build Content-Based similar-movie pipeline | 4 | 1 | 2026-09-27 | 2026-09-27 | High | Not Started | 0 | 3.1 | movies genres + tags | 1) Build feature representation 2) Compute similarity 3) Select Top-M neighbors 4) Persist Similar-Movie Lists | Precomputed Similar-Movie Lists | Given a movieId, system returns valid similar movies | Sample movie lookup; similarity output | 3.5 / Person 2
3.4 | Phase 3 - Modeling | Person 1 | Train ALS and precompute personalized Top-N | 4 | 2 | 2026-09-27 | 2026-09-28 | Critical | Not Started | 0 | 3.1 | userId, movieId, rating from train data | 1) Configure ALS 2) Train 3) Generate candidates 4) Remove already-rated 5) Rank 6) Precompute Top-N | ALS model + Precomputed ALS Top-N | Model trains reproducibly; sample user returns valid Top-N | ALS config; model metrics; sample Top-N | 3.5 / Person 2
3.5 | Phase 3 - Modeling | Person 1 | Evaluate models by task and prepare serving artifacts | 5 | 1 | 2026-09-28 | 2026-09-28 | Critical | Not Started | 0 | 3.2,3.3,3.4 | Baseline/Content/ALS outputs + test data | 1) Movie Mean vs ALS -> RMSE 2) Popularity/Content/ALS -> Recall@K/NDCG@K 3) Validate artifact schemas 4) Add modelVersion/generatedAt | Evaluation table + production-ready serving artifacts | Metrics complete; artifacts conform to contract; downstream readable | metrics.csv; popularity_topn; similar_movies; als_topn | HANDOFF to Person 2
4.1 | Phase 4 - Online Serving | Person 2 | Load real serving artifacts into MongoDB | 5 | 1 | 2026-09-28 | 2026-09-28 | Critical | Not Started | 0 | 3.5 | Popularity Top-N + Similar-Movie Lists + ALS Top-N | 1) Replace mock data 2) Validate documents 3) Upsert/index 4) Read-back by access pattern | MongoDB with real serving artifacts | All artifact types query correctly; modelVersion visible | Insert logs; sample queries; document screenshots | 4.2
4.2 | Phase 4 - Online Serving | Person 2 | Complete online candidate retrieval, exclusion, fusion and Top-N | 5 | 2 | 2026-09-28 | 2026-09-29 | Critical | Not Started | 0 | 2.4,4.1 | MongoDB + router | 1) Retrieve strategy source 2) Exclude latest already-rated 3) Optional fusion/re-rank 4) Return Top-N with strategy/modelVersion | End-to-end online recommendation | 0/Few/Enough cases return final Top-N and no already-rated items | API traces; before/after exclusion; Top-N outputs | 5.1
5.1 | Phase 5 - Streaming | Person 2 | Set up Kafka rating-event flow | 6 | 1 | 2026-09-29 | 2026-09-29 | High | Not Started | 0 | 0.1 | Rating event schema | 1) Create topic 2) Producer sends userId/movieId/rating/timestamp 3) Consumer/read test 4) Record offsets/logs | Working Kafka event flow | A rating event can be produced and consumed end-to-end | Producer log; consumer output | 5.2
5.2 | Phase 5 - Streaming | Person 2 | Implement Structured Streaming validation and state update | 6 | 2 | 2026-09-29 | 2026-09-30 | Critical | Not Started | 0 | 5.1,1.3 | Kafka events + curated target + MongoDB | 1) readStream 2) Parse schema 3) Validate rating/type/timestamp 4) Update user_history 5) Append validated event to curated data/checkpoint | Validated stream + updated user history + updated curated data | Request after rating sees new history; new event persisted for retraining | Streaming logs; MongoDB before/after; curated read-back | 6.1
6.1 | Phase 6 - Model Refresh | Both | Connect streaming feedback to scheduled retraining | 7 | 1 | 2026-09-30 | 2026-09-30 | Critical | Not Started | 0 | 5.2,3.5 | Updated curated data + training pipeline | 1) Person 2 triggers job 2) Person 1 retrains/evaluates 3) Produce candidate version 4) Store metrics/artifacts | Candidate Model Version | New data is included and candidate outputs are reproducible | Job log; candidate version; metrics | 6.2
6.2 | Phase 6 - Model Refresh | Both | Implement promotion gate and publish/rollback logic | 7 | 1 | 2026-09-30 | 2026-09-30 | High | Not Started | 0 | 6.1 | Candidate metrics + active model metadata | 1) Compare acceptance criteria 2) Fail -> keep current 3) Pass -> publish new artifacts 4) Update active modelVersion | Promotion result + active version | Fail path preserves old serving; pass path activates new version cleanly | Gate result; active version before/after | 7.1
7.1 | Phase 7 - Performance & Reproducibility | Person 1 | Run controlled performance experiment + reproducibility package | 8 | 1 | 2026-10-01 | 2026-10-01 | Medium | Not Started | 0 | 1.3,2.1 | CSV/Parquet + fixed Spark config | 1) Fix hardware/config/query 2) Warm-up 3) 3-5 measured runs 4) Compare median 5) Capture plans 6) Record versions/seeds/commands | Performance evidence + reproducibility manifest | Experiment controlled; no invented results; another member can rerun | Timing table; Spark config; requirements; commands | 8.1
7.2 | Phase 7 - Performance & Reproducibility | Person 2 | Run serving/streaming validation and failure-path checks | 8 | 1 | 2026-10-01 | 2026-10-01 | Medium | Not Started | 0 | 4.2,5.2,6.2 | Online API + Kafka/Streaming + promotion flow | 1) Test invalid event 2) Test missing user 3) Test stale artifact exclusion 4) Test promotion fail/pass 5) Capture evidence | System validation evidence | Critical failure paths behave predictably | Test matrix; logs; screenshots | 8.1
8.1 | Phase 8 - Integration & Demo | Both | Full end-to-end integration test and demo rehearsal | 9 | 1 | 2026-10-02 | 2026-10-02 | Critical | Not Started | 0 | 7.1,7.2 | All components | 1) Historical batch run 2) Recommendation request 3) New rating event 4) User history update 5) Retraining candidate 6) Promotion demonstration | Stable end-to-end demo flow | No broken interface; demo reproducible from README | Demo checklist; logs; final screenshots | 8.2
8.2 | Phase 8 - Integration & Demo | Both | Evidence pack, freeze, handover for report/slides | 10 | 1 | 2026-10-03 | 2026-10-03 | Critical | Not Started | 0 | 8.1 | Final code + outputs | 1) Collect metrics 2) Query plans 3) MongoDB R/W evidence 4) Streaming logs 5) Architecture screenshots 6) Freeze version/tag | Final evidence pack + release tag | Every rubric claim has evidence; code/config frozen | Evidence folder; release tag; checklist | Report/Slide owner
Formulas:
Start Date = '07_Settings'!$B4+[Start Day]-1
Due Date = [Start Date]+[Duration]-1

## 03_Person_1
PERSON 1 — DATA & RECOMMENDATION MODELING
WBS | Phase | Task | Start | Due | Priority | Status | % Complete | Dependency | Input | Output | Definition of Done | Evidence | Handoff
0.1 | Phase 0 - Setup | Lock architecture, repo, folder structure, config, naming conventions | 2026-09-24 | 2026-09-24 | Critical | Not Started | 0 | - | Final architecture + project requirements | Repo + README + config + agreed folder structure | Both members can clone/run skeleton; config paths work | README screenshot; repo structure; environment versions | Both
0.2 | Phase 0 - Setup | Freeze data contract and serving artifact contract | 2026-09-24 | 2026-09-24 | Critical | Not Started | 0 | 0.1 | Architecture + MovieLens schema | Signed-off schema contracts | Person 2 can consume mock artifacts without manual edits | Schema document; sample JSON/CSV | Both
1.1 | Phase 1 - Data Foundation | Ingest MovieLens CSV with explicit PySpark schemas | 2026-09-24 | 2026-09-24 | Critical | Not Started | 0 | 0.1 | ratings.csv, movies.csv, tags.csv, links.csv | ratings_df, movies_df, tags_df, links_df | Schemas/types correct; row counts captured; no silent inference | Schema print; row counts; sample rows | 1.2
1.2 | Phase 1 - Data Foundation | Clean, transform and join core datasets | 2026-09-25 | 2026-09-25 | Critical | Not Started | 0 | 1.1 | Raw DataFrames | Clean/enriched DataFrames | No unresolved critical quality issue; joins validated | Quality summary; before/after counts; join checks | 1.3
1.3 | Phase 1 - Data Foundation | Write Curated Parquet and read-back validation | 2026-09-25 | 2026-09-25 | Critical | Not Started | 0 | 1.2 | Clean DataFrames | Curated Parquet | Read-back succeeds; schema/counts consistent | Parquet paths; read-back output; row counts | Person 1 analytics + Person 2 streaming append target
2.1 | Phase 2 - Analytics & Validation | Build Spark SQL analytics and inspect execution plans | 2026-09-26 | 2026-09-26 | High | Not Started | 0 | 1.3 | Curated Parquet | Analytics results + execution-plan evidence | At least 2 meaningful SQL analyses + formatted plan interpretation | Query outputs; explain plan; screenshots | Report / evidence
2.2 | Phase 2 - Analytics & Validation | Implement MapReduce statistics and cross-check with Spark | 2026-09-26 | 2026-09-26 | Medium | Not Started | 0 | 1.2 | Clean ratings text/CSV or compatible input | MapReduce statistics | Reducer output matches Spark within expected tolerance | Mapper/reducer code; comparison table | Report / evidence
3.1 | Phase 3 - Modeling | Create train/validation/test evaluation setup | 2026-09-26 | 2026-09-26 | Critical | Not Started | 0 | 1.3 | Curated ratings | train_df, val_df, test_df + evaluation rules | Split reproducible; no leakage; relevant-item rule documented | Split counts; seed/config; rule definition | 3.2 / 3.3 / 3.4
3.2 | Phase 3 - Modeling | Build Movie Mean and Popularity baselines | 2026-09-26 | 2026-09-26 | High | Not Started | 0 | 3.1 | Train data | Movie Mean baseline + Popularity Top-N | Predictions exist; Popularity Top-N valid and deterministic | Baseline metrics; sample Top-N | 3.5 / Person 2
3.3 | Phase 3 - Modeling | Build Content-Based similar-movie pipeline | 2026-09-27 | 2026-09-27 | High | Not Started | 0 | 3.1 | movies genres + tags | Precomputed Similar-Movie Lists | Given a movieId, system returns valid similar movies | Sample movie lookup; similarity output | 3.5 / Person 2
3.4 | Phase 3 - Modeling | Train ALS and precompute personalized Top-N | 2026-09-27 | 2026-09-28 | Critical | Not Started | 0 | 3.1 | userId, movieId, rating from train data | ALS model + Precomputed ALS Top-N | Model trains reproducibly; sample user returns valid Top-N | ALS config; model metrics; sample Top-N | 3.5 / Person 2
3.5 | Phase 3 - Modeling | Evaluate models by task and prepare serving artifacts | 2026-09-28 | 2026-09-28 | Critical | Not Started | 0 | 3.2,3.3,3.4 | Baseline/Content/ALS outputs + test data | Evaluation table + production-ready serving artifacts | Metrics complete; artifacts conform to contract; downstream readable | metrics.csv; popularity_topn; similar_movies; als_topn | HANDOFF to Person 2
6.1 | Phase 6 - Model Refresh | Connect streaming feedback to scheduled retraining | 2026-09-30 | 2026-09-30 | Critical | Not Started | 0 | 5.2,3.5 | Updated curated data + training pipeline | Candidate Model Version | New data is included and candidate outputs are reproducible | Job log; candidate version; metrics | 6.2
6.2 | Phase 6 - Model Refresh | Implement promotion gate and publish/rollback logic | 2026-09-30 | 2026-09-30 | High | Not Started | 0 | 6.1 | Candidate metrics + active model metadata | Promotion result + active version | Fail path preserves old serving; pass path activates new version cleanly | Gate result; active version before/after | 7.1
7.1 | Phase 7 - Performance & Reproducibility | Run controlled performance experiment + reproducibility package | 2026-10-01 | 2026-10-01 | Medium | Not Started | 0 | 1.3,2.1 | CSV/Parquet + fixed Spark config | Performance evidence + reproducibility manifest | Experiment controlled; no invented results; another member can rerun | Timing table; Spark config; requirements; commands | 8.1
8.1 | Phase 8 - Integration & Demo | Full end-to-end integration test and demo rehearsal | 2026-10-02 | 2026-10-02 | Critical | Not Started | 0 | 7.1,7.2 | All components | Stable end-to-end demo flow | No broken interface; demo reproducible from README | Demo checklist; logs; final screenshots | 8.2
8.2 | Phase 8 - Integration & Demo | Evidence pack, freeze, handover for report/slides | 2026-10-03 | 2026-10-03 | Critical | Not Started | 0 | 8.1 | Final code + outputs | Final evidence pack + release tag | Every rubric claim has evidence; code/config frozen | Evidence folder; release tag; checklist | Report/Slide owner
Formulas:
Start = INDEX('02_Master_Plan'!G:G,MATCH([WBS],'02_Master_Plan'!A:A,0))
Due = INDEX('02_Master_Plan'!H:H,MATCH([WBS],'02_Master_Plan'!A:A,0))

## 04_Person_2
PERSON 2 — SERVING, STREAMING & INTEGRATION
WBS | Phase | Task | Start | Due | Priority | Status | % Complete | Dependency | Input | Output | Definition of Done | Evidence | Handoff
0.1 | Phase 0 - Setup | Lock architecture, repo, folder structure, config, naming conventions | 2026-09-24 | 2026-09-24 | Critical | Not Started | 0 | - | Final architecture + project requirements | Repo + README + config + agreed folder structure | Both members can clone/run skeleton; config paths work | README screenshot; repo structure; environment versions | Both
0.2 | Phase 0 - Setup | Freeze data contract and serving artifact contract | 2026-09-24 | 2026-09-24 | Critical | Not Started | 0 | 0.1 | Architecture + MovieLens schema | Signed-off schema contracts | Person 2 can consume mock artifacts without manual edits | Schema document; sample JSON/CSV | Both
1.4 | Phase 1 - Data Foundation | Create MongoDB serving schema using mock artifacts | 2026-09-24 | 2026-09-25 | High | Not Started | 0 | 0.2 | Serving artifact contract | MongoDB serving skeleton | Mock artifacts can be inserted/read with target access patterns | Collection list; index list; sample read-back | 2.4 / 3.1
2.3 | Phase 2 - Analytics & Validation | Build Recommendation API skeleton + User History Check | 2026-09-25 | 2026-09-26 | High | Not Started | 0 | 1.4 | MongoDB mock serving store | Working API skeleton | Given userId, API returns valid history tier | API request/response samples; logs | 2.4
2.4 | Phase 2 - Analytics & Validation | Implement 0/Few/Enough history router with mock data | 2026-09-26 | 2026-09-26 | Critical | Not Started | 0 | 2.3 | API skeleton + mock artifacts | History-based switching logic | All three paths return candidates from correct sources | 3 test cases; routing logs | 3.2 / 4.2
4.1 | Phase 4 - Online Serving | Load real serving artifacts into MongoDB | 2026-09-28 | 2026-09-28 | Critical | Not Started | 0 | 3.5 | Popularity Top-N + Similar-Movie Lists + ALS Top-N | MongoDB with real serving artifacts | All artifact types query correctly; modelVersion visible | Insert logs; sample queries; document screenshots | 4.2
4.2 | Phase 4 - Online Serving | Complete online candidate retrieval, exclusion, fusion and Top-N | 2026-09-28 | 2026-09-29 | Critical | Not Started | 0 | 2.4,4.1 | MongoDB + router | End-to-end online recommendation | 0/Few/Enough cases return final Top-N and no already-rated items | API traces; before/after exclusion; Top-N outputs | 5.1
5.1 | Phase 5 - Streaming | Set up Kafka rating-event flow | 2026-09-29 | 2026-09-29 | High | Not Started | 0 | 0.1 | Rating event schema | Working Kafka event flow | A rating event can be produced and consumed end-to-end | Producer log; consumer output | 5.2
5.2 | Phase 5 - Streaming | Implement Structured Streaming validation and state update | 2026-09-29 | 2026-09-30 | Critical | Not Started | 0 | 5.1,1.3 | Kafka events + curated target + MongoDB | Validated stream + updated user history + updated curated data | Request after rating sees new history; new event persisted for retraining | Streaming logs; MongoDB before/after; curated read-back | 6.1
6.1 | Phase 6 - Model Refresh | Connect streaming feedback to scheduled retraining | 2026-09-30 | 2026-09-30 | Critical | Not Started | 0 | 5.2,3.5 | Updated curated data + training pipeline | Candidate Model Version | New data is included and candidate outputs are reproducible | Job log; candidate version; metrics | 6.2
6.2 | Phase 6 - Model Refresh | Implement promotion gate and publish/rollback logic | 2026-09-30 | 2026-09-30 | High | Not Started | 0 | 6.1 | Candidate metrics + active model metadata | Promotion result + active version | Fail path preserves old serving; pass path activates new version cleanly | Gate result; active version before/after | 7.1
7.2 | Phase 7 - Performance & Reproducibility | Run serving/streaming validation and failure-path checks | 2026-10-01 | 2026-10-01 | Medium | Not Started | 0 | 4.2,5.2,6.2 | Online API + Kafka/Streaming + promotion flow | System validation evidence | Critical failure paths behave predictably | Test matrix; logs; screenshots | 8.1
8.1 | Phase 8 - Integration & Demo | Full end-to-end integration test and demo rehearsal | 2026-10-02 | 2026-10-02 | Critical | Not Started | 0 | 7.1,7.2 | All components | Stable end-to-end demo flow | No broken interface; demo reproducible from README | Demo checklist; logs; final screenshots | 8.2
8.2 | Phase 8 - Integration & Demo | Evidence pack, freeze, handover for report/slides | 2026-10-03 | 2026-10-03 | Critical | Not Started | 0 | 8.1 | Final code + outputs | Final evidence pack + release tag | Every rubric claim has evidence; code/config frozen | Evidence folder; release tag; checklist | Report/Slide owner
Formulas:
Start = INDEX('02_Master_Plan'!G:G,MATCH([WBS],'02_Master_Plan'!A:A,0))
Due = INDEX('02_Master_Plan'!H:H,MATCH([WBS],'02_Master_Plan'!A:A,0))

## 05_Milestones
MILESTONES, HANDOFFS & ACCEPTANCE GATES
ID | Milestone / Handoff | Owner | Target Day | Input | Output | Acceptance Gate | Consumer | Status
M0 | Architecture + contracts frozen | Both | 1 | Final architecture | Repo + data/artifact contracts | Both members agree and can run skeleton | Both | Not Started
M1 | Curated Data Ready | Person 1 | 2 | MovieLens CSV | Validated Curated Parquet | Read-back + schema/count validation | Modeling + Streaming | Not Started
M2 | Offline Models Ready | Person 1 | 5 | Curated data | Baselines + Content + ALS + metrics | RMSE + Recall@K/NDCG@K + artifacts valid | Person 2 | Not Started
M3 | Serving Integration Ready | Person 2 | 6 | Real serving artifacts | MongoDB + API + routing + final Top-N | 0/Few/Enough cases work; no already-rated items | Integration | Not Started
M4 | Streaming Feedback Ready | Person 2 | 7 | Rating event | Kafka + Structured Streaming + history update | New rating appears in history and curated data | Retraining | Not Started
M5 | Model Refresh Ready | Both | 7 | Updated curated data | Candidate model + promotion result | Fail keeps current; pass publishes new version | Integration | Not Started
M6 | Performance & Validation Ready | Both | 8 | Full system | Perf/repro/test evidence | Controlled experiment + failure checks complete | Final demo | Not Started
M7 | Final End-to-End Demo | Both | 9 | All components | Stable demo flow | Historical → serving → feedback → refresh demonstrated | Report/Slides | Not Started
M8 | Final Freeze / Evidence Pack | Both | 10 | Final code/results | Release tag + evidence folder | Every claim backed by evidence | Submission | Not Started

## 06_Risks
RISK & ISSUE REGISTER
ID | Risk / Issue | Category | Probability | Impact | Score | Owner | Mitigation / Next Action | Trigger / Evidence | Status
R1 | Person 1 becomes bottleneck because data + modeling workload is heavy | Capacity | 4 | 5 | 20 | Both | Use mock artifact contract so Person 2 builds in parallel; freeze scope after core pipeline | Person 1 slips > 1 day | Open
R2 | Serving artifact schema changes late and breaks MongoDB/API | Integration | 3 | 5 | 15 | Both | Freeze contract on Day 1; version schemas; validate before handoff | Manual field renaming required | Open
R3 | MapReduce input format does not match Parquet implementation | Technical | 3 | 3 | 9 | Person 1 | Use cleaned ratings CSV/Text for Hadoop Streaming if direct Parquet is unsupported | MR job cannot read curated format | Monitoring
R4 | Streaming is overbuilt before core batch/model pipeline works | Scope | 3 | 4 | 12 | Person 2 | Prioritize core serving and use minimal Kafka/Structured Streaming demo | Core ALS/serving not ready by Day 5 | Open
R5 | Evaluation leakage or incorrect ranking ground truth | Model Quality | 2 | 5 | 10 | Person 1 | Freeze split method, seed, relevant-item threshold before modeling | Unexpectedly perfect metrics / inconsistent reruns | Open
R6 | Cold-start thresholds treated as universal truth | Design | 2 | 3 | 6 | Both | Label thresholds as configurable design parameters and test cases | Defense question challenges threshold choice | Monitoring
R7 | Candidate model auto-deployed without gate | Operations | 2 | 5 | 10 | Person 2 | Keep current active model until explicit pass | Active version changes before validation | Open
R8 | Evidence missing although code works | Delivery | 4 | 4 | 16 | Both | Evidence is part of Definition of Done; capture during each task | Final week requires re-running everything | Open

## 07_Settings
PROJECT CONTROL SETTINGS
Project | MovieLens Hybrid Recommendation System
Sprint Start Date | 2026-09-24
Sprint Length (days) | 10
Project Manager | Project Lead
Person 1 | Data & Recommendation Modeling
Person 2 | Serving, Streaming & Integration
Progress Formula | Based on task % complete
Definition of Done | Code runs + output correct + evidence + downstream can consume
Status | Priority | Owner | Risk Status
Not Started | Critical | Person 1 | Open
In Progress | High | Person 2 | Monitoring
Blocked | Medium | Both | Closed
Done